## Using this Spreadsheet
Konigi Schedule & Cost Summary Calculator
About This Document
This Cost Estimate and Scheduling spreadsheet provides a lightweight method for learning to estimate time to complete a web design project, and calculating cost for completion. The intended audience is freelancers or individual contractors. The purpose of the document is to get acquainted with Excel as a tool for cost estimation, with the hopes that you will learn to use and modify it to suit your needs. This is only a learning tool.
Disclaimer
Use of this spreadsheet is at your own risk. Michael Angeles and Konigi provide no guarantee for the use of this spreadsheet. By electing to use this spreadsheet, the user acknowledges that any errors are the sole responsibility of the use due to data entry, formula creation, calculation, or any use of this spreadsheet on the user's part.
For instructions on using this document, please refer to the information at:
http://konigi.com/tools/schedule-and-cost-summary-calculator

## Hoja1
IgniteCrowd |  |  | Gastos | Mes | Día
Actividades | Duración (Días) | Hora por día (8 horas max) | Transporte | 2640 | 120
Descubrimiento e investigación | 40 |  | Comida | 6600 | 300
Conocer al usuario | 11 |  | Internet | 550 | 25
Diseñar encuesta/entrevista | 2 | 4 | Luz | 1210 | 55
Aplicar encuesta/entrevista | 3 | 4 | Renta | 10000 | 454.5
Analizar resultados | 2 | 3 | Agua | 220 | 10
Crear el perfil | 1 | 5 | Limpieza | 5500 | 250
Crear persona | 1 | 5 | Basura | 50 | 2.2727
Crear escenario | 2 | 4 | Agua potable | 352 | 16
Investigación de negocios |  |  | Salario | 99000 | 4500 | *5 miembros | $900 el día
Realizar un estudio de mercado | 5 | 5 | Recursos y herramientas | 2200 | 100
Analizar resultados del mercado | 5 | 4 | Total | 128322 | 5832.7727
Documentación ERS
Definir los requerimientos funcionales | 4 | 3
Definir los requerimientos no funcionales | 4 | 3
Diseño de software | 7 |  | Total duración | Total gastos
Diagramas UML | 7 | 4 | 110 | 641604.997
Soluciones de diseño | 9
Definir una paleta de colores para el sistema | 1 | 4
Realizar boceto | 2 | 5
Realizar mockups de las interfaces | 4 | 5
Adaptabilidad de visualización | 2 | 8
Desarrollo de software | 44
Programación | 44 | 8
Evaluar diseño frente a los requerimientos | 10
Realizar pruebas de unidad e integración | 4 | 6
Realizar la verificación de los requerimientos | 3 | 5
Validar el diseño y el funcionamiento | 2 | 5
Comparar resultados con el diseño inicial | 1 | 8
Total | 110